## Udacity CICD Plan
Original Plan - Project 2 CICD
Date | Task
2021-10-22 | Clone repository
2021-10-23 | Raise a virtual python enviroment
2021-10-24 | In a bash console I activate the new enviroment
2021-10-25 | Stand on the path that corresponds and inside enviroment use the make all
2021-10-26 | Run Flask Run
2021-10-27 | We create a web app
2021-10-28 | Download Azure tools to deploy
2021-10-29 | Deploy to the new webapp
2021-10-30 | Build the pipeline in azure devops
2021-10-31 | Test from sh file and / or postman
2021-11-01 | Test full flow
2021-11-02 | Write Readme
Original Plan - Project 2 CICD
Date | Task
2021-10-22 | -
2021-10-23 | -
2021-10-24 | -
2021-10-25 | -
2021-10-26 | -
2021-10-27 | -
2021-10-28 | -
2021-10-29 | -
2021-10-30 | Clone repository Build makefile Ssh connection
2021-10-31 | Raise a virtual python enviroment In a bash console I activate the new enviroment
2021-11-01 | Run Flask Run
2021-11-02 | -
2021-11-03 | -
2021-11-04 | -
2021-11-05 | -
2021-11-06 | -
2021-11-07 | We create a web app Download Azure tools to deploy Deploy to the new webapp
2021-11-08 | Build the pipeline in azure devops Test from sh file and / or postman Test full flow
2021-11-09 | Write Readme First delivery Project