## Udacity CICD Plan Semanal
Original Plan - Project 2 CICD
Date | Task | Tiempo HH
2021-10-22 | Clone repository | 1
2021-10-23 | Raise a virtual python enviroment | 2
2021-10-24 | In a bash console I activate the new enviroment | 1
2021-10-25 | Stand on the path that corresponds and inside enviroment use the make all | 1
2021-10-26 | Run Flask Run | 1
2021-10-27 | We create a web app | 1
2021-10-28 | Download Azure tools to deploy | 1
2021-10-29 | Deploy to the new webapp | 1
2021-10-30 | Build the pipeline in azure devops | 2
2021-10-31 | Test from sh file and / or postman | 1
2021-11-01 | Test full flow | 1
2021-11-02 | Write Readme | 3
Original Plan - Project 2 CICD
Date | Task
2021-10-22 | -
2021-10-23 | -
2021-10-24 | -
2021-10-25 | -
2021-10-26 | -
2021-10-27 | -
2021-10-28 | -
2021-10-29 | -
2021-10-30 | Clone repository Build makefile Ssh connection | 2
2021-10-31 | Raise a virtual python enviroment In a bash console I activate the new enviroment | 2
2021-11-01 | Run Flask Run | 1
2021-11-02 | -
2021-11-03 | -
2021-11-04 | -
2021-11-05 | -
2021-11-06 | -
2021-11-07 | We create a web app Download Azure tools to deploy Deploy to the new webapp | 2
2021-11-08 | Build the pipeline in azure devops Test from sh file and / or postman Test full flow | 3
2021-11-09 | Write Readme First delivery Project | 3

## Udacity CICD Plan Trimestral
Year | Trim. | Task | Tiempo HH
2021 | 1 | Udacity Devops on Microsoft Azure course application | 3
| 2 | Analysis of application and evaluation of candidates | 4
| 3 | Welcome, induction and planning. | 2
| 4 | Beginning, development and completion of the course. | 62
2022 | 1 | Find next course to deepen the knowledge of Devops. | 4